## LoginLogout
IBCS-Primax Software (Bangladesh) Limited- Final Project
Project Name | Insurance Broker System | Test Summary |  |  | Key (Test Status)
Project Link | https://demo.guru99.com/insurance/v1/index.php |  | No. of Features: | 3 | Pending | New test cases that has not been started yet
Environment | Web Application (Tested on Chrome) |  | No. of Test Cases: | 5 | On Hold | Project/Module/Feature put on hold
Assigned To | Usrah Saba |  | No. of Tested Cases: | 5 | Tested | Particular test cases has been tested
Test Item Name | Login Functionality |  | No. of Untested Cases: | 0 | Re-tested | Original test case failed and has been retested
Test Type | System testing(Black Box) |  | No. of Re-tested Cases: | 0 | Key Test (Result)
Test Objective | To verify that the login functionality allows registered users to access their accounts with valid credentials and restricts access for invalid credentials. |  | No. of On Hold Test Cases: | 0 | Pass | Test case achived the expected result
Total Test Cases | 23 |  | No. of Pending Test Cases: | 0 | Fail | Test cases failed to meet the expectation result
Start Date | 2025-03-08 |  | No of Passed Test Cases: | 5 | N/A
|  |  | No. of Failed Test Cases: | 0
Test Case Description | [5 empty] | Test Execution[ This column to be filled up while executing the test case]
Test Case id | Test Case Title | Precondition | Test case data | Steps to perform Test Case/Test Script | Expected Results | Actual Results | Pass/Fail | Comments | Priority | Test Cycle No. | Test Date | Test Status
IBS_login_1 | Valid Login Functionality | 1.The user must have a registered account on the website. 2. The user should navigate to the login panel | Email: usrahsaba07@gmail.com Password: 6666 | 1. Open the login page. 2. Enter a valid email and password. 3. Click "Log in". | User should be successfully logged in. | As Expected | Pass |  | High | 1 | 2025-03-08 | Tested
IBS_login_2 | Verify Invalid Credentials | 1.The user must have a registered account on the website. 2. The user should navigate to the login panel | N/A | 1. Open the login page. 2. Enter an invalid email and password. 3. Click "Log in". | Error message: "Enter your Email address and password correct" | As Expected | Pass |  | High | 1 | 2025-03-08 | Tested
IBS_login_3 | Verify Empty Login Behavior | 1.The user must have a registered account on the website. 2. The user should navigate to the login panel | N/A | 1. Open the login page. 2. Leave both fields empty. 3. Click "Log in". | Error message: "Enter your Email address and password correct" | As Expected | Pass | Error message prompting user to fill required fields. | High | 1 | 2025-03-08 | Tested
IBS_login_4 | Buttons Clickability | 1.The user must have a registered account on the website. 2. The user should navigate to the login panel | N/A | 1. Open the login page. 2. Verify if the "Log in" button is clickable when fields are empty. | Button should be disabled until both fields are filled. | As Expected | Pass |  | Medium | 1 | 2025-03-08 | Tested
IBS_login_5 | Verify Logout Functionality | 1. The user should navigate to the log out area | N/A | Navigate & Click the logout button | The user should be logged out and redirected to the login page. | As Expected | Pass |  | High | 1 | 2025-03-08 | Tested

## Edit Profile
IBCS-Primax Software (Bangladesh) Limited- Final Project
Project Name | Insurance Broker System | Test Summary |  |  | Key (Test Status)
Project Link | https://demo.guru99.com/insurance/v1/index.php |  | No. of Features: | 10 | Pending | New test cases that has not been started yet
Environment | Web Application (Tested on Chrome) |  | No. of Test Cases: | 7 | On Hold | Project/Module/Feature put on hold
Assigned To | Usrah Saba |  | No. of Tested Cases: | 3 | Tested | Particular test cases has been tested
Test Item Name | Edit Profile Functionality |  | No. of Untested Cases: |  | Re-tested | Original test case failed and has been retested
Test Type | System testing(Black Box) |  | No. of Re-tested Cases: |  | Key Test (Result)
Test Objective | To verify that users can successfully update their profile informations |  | No. of On Hold Test Cases: |  | Pass | Test case achived the expected result
Total Test Cases | 23 |  | No. of Pending Test Cases: | 4 | Fail | Test cases failed to meet the expectation result
Start Date | 2025-03-08 |  | No of Passed Test Cases: | 1 | N/A
|  |  | No. of Failed Test Cases: | 6
Test Case Description | [5 empty] | Test Execution[ This column to be filled up while executing the test case]
Test Case id | Test Case Title | Precondition | Test case data | Steps to perform Test Case/Test Script | Expected Results | Actual Results | Pass/Fail | Comments | Priority | Test Cycle No. | Test Date | Test Status
EditProfile_01 | Verify Profile Update'' Functionality | User should logged into the account and navigates to the edit profile panel | N/A | 1. Open profile edit page. 2. Enter valid details. 3. Click "Update User". | Profile should update successfully with a success message. | The profile update button is not responding, and no success message is displayed. | Fail |  | High | 1 | 2025-03-08 | Tested
EditProfile_02 | Verify required fields validation | User should navigate to the edit profile panel | N/A | 1. Leave one or more required fields empty 2. Try to submit the form. | The system should show an error message indicating the missing required fields. All required fields should be validated before submission | The form is submitted without showing any validation errors. | Fail |  | Medium | 1 | 2025-03-08 | Pending
EditProfile_03 | Validate phone number format | User should navigate to the edit profile panel | Phone: 0123456 | 1. Open profile edit page. 2. Enter an invalid phone number. 3. Click "Update User". | System should show an error message for invalid phone format. | The system accepts the invalid phone number | Fail |  | Medium | 1 | 2025-03-08 | Pending
EditProfile_04 | Verify DOB Format | User should navigate to the edit profile panel | N/A | 1. Open profile edit page. 2. Enter a future date as DOB. 3. Click "Update User". | System should prevent saving an invalid DOB. | The system does not allow entering a birth year later than 1995. | Fail |  | Medium | 1 | 2025-03-08 | Pending
EditProfile_05 | Dropdown Functionality | User should navigate to the edit profile panel | N/A | 1. Open profile edit page. 2. Select different options 3. Click Update User" | System should save the selected values correctly. | As Expected | Pass |  | Medium | 1 | 2025-03-08 | Tested
EditProfile_06 | Post Code Format | User should navigate to the edit profile panel | Post Code: ABC12345 | 1. Open profile edit page. 2. Enter an invalid post code 3. Click "Update User". | System should show an error message for invalid post code. | The system accepts the invalid postcode | Fail |  | Medium | 1 | 2025-03-08 | Pending
EditProfile_07 | Update Button Clickability | User should navigate to the edit profile panel | N/A | 1. Open profile edit page. 2. fill the fields 3. Click Update User'' | Button should work properly | The "Update" button is non-functional, and the profile information does not update. | Fail | Sometimes a popup asks to save details when navigating to another panel, but selecting "Yes" doesn't save the changes. | Medium | 1 | 2025-03-08 | Tested

## Profile
IBCS-Primax Software (Bangladesh) Limited- Final Project
Project Name | Insurance Broker System | Test Summary |  |  | Key (Test Status)
Project Link | https://demo.guru99.com/insurance/v1/index.php |  | No. of Features: | 1 | Pending | New test cases that has not been started yet
Environment | Web Application (Tested on Chrome) |  | No. of Test Cases: | 3 | On Hold | Project/Module/Feature put on hold
Assigned To | Usrah Saba |  | No. of Tested Cases: | 3 | Tested | Particular test cases has been tested
Test Item Name | Profile Functionality |  | No. of Untested Cases: | 0 | Re-tested | Original test case failed and has been retested
Test Type | System testing(Black Box) |  | No. of Re-tested Cases: | 0 | Key Test (Result)
Test Objective | To verify if the data is displayed accurately on the profile page |  | No. of On Hold Test Cases: | 0 | Pass | Test case achived the expected result
Total Test Cases | 23 |  | No. of Pending Test Cases: | 0 | Fail | Test cases failed to meet the expectation result
Start Date | 2025-03-08 |  | No of Passed Test Cases: | 0 | N/A
|  |  | No. of Failed Test Cases: | 3
Test Case Description | [5 empty] | Test Execution[ This column to be filled up while executing the test case]
Test Case id | Test Case Title | Precondition | Test case data | Steps to perform Test Case/Test Script | Expected Results | Actual Results | Pass/Fail | Comments | Priority | Test Cycle No. | Test Date | Test Status
Profile_1 | Check Profile'' Section Visibility | User should be in Profile'' Panel | N/A | Navigate to the Profile Header | Profile section should display user details | profile'' section is non-functional, and no user details are shown | Fail |  | High | 1 | 2025-03-08 | Tested
Profile_2 | Profile Data Empty Fields Check | User should be in Profile'' Panel | N/A | Verify if any fields are empty. | System should display a default message for missing data | No data displayed for the fields | Fail |  | High | 1 | 2025-03-08 | Tested
Profile_3 | Profile Data Accuracy | User should be in Profile'' Panel | N/A | Verify if the profile data shown matches the expected data accurately | The profile should display the data without any errors | No data is shown in any field | Fail |  | High | 1 | 2025-03-08 | Tested

## Request Quotation
IBCS-Primax Software (Bangladesh) Limited- Final Project
Project Name | Insurance Broker System | Test Summary |  |  | Key (Test Status)
Project Link | https://demo.guru99.com/insurance/v1/index.php |  | No. of Features: | 11 | Pending | New test cases that has not been started yet
Environment | Web Application (Tested on Chrome) |  | No. of Test Cases: | 5 | On Hold | Project/Module/Feature put on hold
Assigned To | Usrah Saba |  | No. of Tested Cases: | 5 | Tested | Particular test cases has been tested
Test Item Name | Generate Quotation request |  | No. of Untested Cases: |  | Re-tested | Original test case failed and has been retested
Test Type | System testing(Black Box) |  | No. of Re-tested Cases: |  | Key Test (Result)
Test Objective | To verify that users can successfully generate a quotation request by providing the required information |  | No. of On Hold Test Cases: |  | Pass | Test case achived the expected result
Total Test Cases | 23 |  | No. of Pending Test Cases: |  | Fail | Test cases failed to meet the expectation result
Start Date | 2025-03-08 |  | No of Passed Test Cases: | 5 | N/A
|  |  | No. of Failed Test Cases: | 0
Test Case Description | [5 empty] | Test Execution[ This column to be filled up while executing the test case]
Test Case id | Test Case Title | Precondition | Test case data | Steps to perform Test Case/Test Script | Expected Results | Actual Results | Pass/Fail | Comments | Priority | Test Cycle No. | Test Date | Test Status
RQ_1 | Verify ''Request Quotation'' Functionality With Valid Data | User should be in Request Quotation Panel | N/A | 1. Check if the dropdown selection matches the chosen option. 2. Fill in all the required information. 3. Click the "Update User" button. | The system should save the quotation and display a success message | As Expected | Pass |  | High | 1 | 2025-03-08 | Tested
RQ_2 | Verify ''Request Quotation'' Functionality With Invalid Data | User should be in Request Quotation Panel | N/A | 1.Enter incorrect or missing values 2. Click "Save Quotation | The system should show validation messages indicating incorrect or missing data. | The system accepts invalid data and assigns an ID | Fail |  | High | 1 | 2025-03-08 | Tested
RQ_3 | Verify Reset'' Button Functionality | User should be in Request Quotation Panel | N/A | 1. Enter values 2. Click on Reset Button'' | 1. System Should Reset all the entered Values 2. System should Calculate and show result | As Expected | Pass |  | Medium | 1 | 2025-03-08 | Tested
RQ_4 | Verify Calculate Premium'' Button Functionality | User should be in Request Quotation Panel | N/A | 1. .Enter Valid EstimatedValues 2. click on Calculate Premium'' Button again 3. enter Invalid Estimated value 4. click on Calculate Permium Button | 1. System Should Reset all the entered Values 2. System should Calculate and show result | As Expected | Pass |  | Medium | 1 | 2025-03-08 | Tested
RQ_5 | DropDOwn Functionality | User should be in Request Quotation Panel | N/A | 1. Click on each dropdown menu 2. Verify if the options appear correctly. 3. Select an option from each dropdown. 4. Ensure the selected value is displayed correctly in the dropdown after selection. | Each dropdown should display all options and keep the selected value | As Expected | Pass |  | High | 1 | 2025-03-08 | Tested

## Retrieve Quotation
IBCS-Primax Software (Bangladesh) Limited- Final Project
Project Name | Insurance Broker System | Test Summary |  |  | Key (Test Status)
Project Link | https://demo.guru99.com/insurance/v1/index.php |  | No. of Features: | 4 | Pending | New test cases that has not been started yet
Environment | Web Application (Tested on Chrome) |  | No. of Test Cases: | 8 | On Hold | Project/Module/Feature put on hold
Assigned To | Usrah Saba |  | No. of Tested Cases: | 8 | Tested | Particular test cases has been tested
Test Item Name | Retieve Quotation Functionality |  | No. of Untested Cases: |  | Re-tested | Original test case failed and has been retested
Test Type | System testing(Black Box) |  | No. of Re-tested Cases: |  | Key Test (Result)
Test Objective | To verify that users can retrieve saved quotations using an identification number and view the correct details. |  | No. of On Hold Test Cases: |  | Pass | Test case achived the expected result
Total Test Cases | 23 |  | No. of Pending Test Cases: |  | Fail | Test cases failed to meet the expectation result
Start Date | 2025-03-08 |  | No of Passed Test Cases: | 5 | N/A
|  |  | No. of Failed Test Cases: | 3
Test Case Description | [5 empty] | Test Execution[ This column to be filled up while executing the test case]
Test Case id | Test Case Title | Precondition | Test case data | Steps to perform Test Case/Test Script | Expected Results | Actual Results | Pass/Fail | Comments | Priority | Test Cycle No. | Test Date | Test Status
RT_Q_1 | Valid Quotation Retrieval | User Should be in Retrieve Quotation Panel | Identification Number- 44230 | 1. enter Valid Identification Number 2. Click Retrieve | The system should fetch and display the quotation details. | As Expected | Pass |  | High | 1 | 2025-03-08 | Tested
RT_Q_2 | Invalid Quotation Retrieval | User Should be in Retrieve Quotation Panel | N/A | 1. Enter Invalid Identification Number 2. Click Retrieve | The system should display an error message indicating invalid input | As Expected | Pass |  | High | 1 | 2025-03-08 | Tested
RT_Q_3 | Empty Quotation Retrieval | User Should be in Retrieve Quotation Panel | N/A | Keep the field blank | The system should not proceed and should show a validation message | As Expected | Pass |  | High | 1 | 2025-03-08 | Tested

## Bug Reports
Bug Reports
Bug Report 1: Profile Section Not Displaying User Details
Bug ID | IBS-BUG-001
Test Case ID | Profile_1
Module | Profile Section
Priority | High
Environment | Web Application (Tested on Chrome)
Description | The "Profile" section does not display any user details after logging in. Users are unable to view their saved information.
Steps to perform Test Case | 1. Log in with valid credentials. 2. Navigate to the Profile section. 3. Observe that no user details are displayed.
Expected Result | The Profile section should display user details such as name, phone, DOB, License type, License period, Occupation, Driver History, address
Actual Result | profile'' section is non-functional, and no user details are shown
Attachments | Attached
Status | need to fix
Bug Report 2: Edit Profile Not Updating User Information
Bug ID | IBS-BUG-002
Test Case ID | EditProfile_01
Module | Edit Profile
Priority | High
Environment | Web Application (Tested on Chrome)
Description | The "Edit Profile" section does not update user details after clicking "Update User." The phone number field also allows invalid input. | After Clicking '"Update User'' =
Steps to perform Test Case | 1. Log in with valid credentials. 2. Navigate to the Edit Profile section. 3. Enter new details. 4. Click on Update User. 5. Refresh the page and check if the details are saved.
Expected Result | The system should save the updated profile details and show a success message.
Actual Result | The profile remains unchanged, and no success message appears. The fields allow invalid digits and special characters.
Attachments | N/A
Status | need to fix
Bug Report 3: Request Quotation Accepting Invalid Data
Bug ID | IBS-BUG-003
Test Case ID | RQ_2
Module | Request Quotation
Priority | High
Environment | Web Application (Tested on Chrome)
Description | The "Request Quotation" form accepts incorrect or incomplete data without showing validation messages and still generates an ID number.
Steps to perform Test Case | 1. Log in and navigate to the Request Quotation page. 2. Enter incorrect or missing values in the required fields. 3. Click on Save Quotation. 4. Observe that the system still generates a quotation ID.
Expected Result | The system should validate input fields and show error messages for missing or incorrect data. It should not generate a quotation ID if the data is invalid.
Actual Result | The system accepts invalid data and assigns an ID
Attachments | screenshots attached
Status | need to fix